## Product Info
Product Vision
Put the product vision here.
Definition of Done
Story | Release
• Story tasks complete | • All stories for the release completed
• Unit tests written and passing | • Full regression testing done and passing
• Acceptance tests defined and passing (automated where practical) | • Exploratory testing done
• Builds without errors or warnings | • No must-fix defects
• No must-fix defects | • Release notes complete
• Release notes updated | • Documentation complete (anything extra, e.g. integration between tools)
• Documentation updated | • Code and documentation branched from main to release branch
• Code and documentation checked in and merged to main branch | • Accepted by customer
• Acceptance criteria satisfied | • Deployed to users
• Nonfunctional requirements satisfied

## Release Plan
Release Plan
Release | Start | Days | End | Points | Status | Release Date
2 | 2013-01-28 | 42 | 2013-03-10 | 20 | In progress
2.1 | 2013-03-11 | 0 | 2013-03-11 | 0
2.2 | 2013-03-11 | 0 | 2013-03-11 | 0
Sprint Plan
Sprint | Start | Days | End | Points | Status | Release | Realized | Actual Average
1 | 2013-01-28 | 14 | 2013-02-10 | 7 | Done | 2 | 7 | 0 | 6
2 | 2013-02-11 | 14 | 2013-02-24 | 5 | Done | 2 | 5 | 1 | 6
3 | 2013-02-25 | 14 | 2013-03-10 | 8 | In progress | 2
4 | 2013-03-11 | 14 | 2013-03-24 | 0
5 | 2013-03-25 | 14 | 2013-04-07 | 0
6 | 2013-04-08 | 14 | 2013-04-21 | 0
Formulas:
Start = [Start, row above]+[Days, row above]
End = IF(ReleasePlan[[#This Row],[Days]]=0,ReleasePlan[[#This Row],[Start]],ReleasePlan[[#This Row],[Start]]+ReleasePlan[[#This Row],[Days]]-1)
End = IF(SprintPlan[[#This Row],[Days]]=0,SprintPlan[[#This Row],[Start]],SprintPlan[[#This Row],[Start]]+SprintPlan[[#This Row],[Days]]-1)

## Product Backlog
Product Backlog
Story | Description | Acceptance Criteria | Priority | Points | Sprint | Status
Story 1 | Description one | • Criteria 1 • Criteria 2 | 1 | 5 | 1 | Done
Story 2 | Description two | • Criteria 1 • Criteria 2 • Criteria 3 | 1 | 5 | 2 | Done
Story 3 | Description three | • Criteria 1 | 2 | 8 | 3 | In progress

## Bugs
Bugs
Title | Description | Acceptance Criteria | Severity | Priority | Points | Sprint | Status
Example bug | Delete this example | • Example acceptance criteria | 3 - Medium | 1 | 2 | 1 | Done

## Sprint 1
Sprint | 1 |  | Goal: This is the goal for the sprint
Days |  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Points Completed |  |  | N/A | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1
Ideal Trend |  |  | 7 | 6.5 | 6 | 5.5 | 5 | 4.5 | 4 | 3.5 | 3 | 2.5 | 2 | 1.5 | 1 | 0.5 | 0
Actual Trend |  |  | 7 | 6 | 6 | 6 | 5 | 5 | 4 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 0
Total points: |  | 7
Sprint days: |  | 14
Points per day: |  | 0.5